## G10
Row | District Donor Project | System Donor Project | Description Donor Project | Donor UPC | District Recipient Project | System Recipient Project | Description Recipient Project | Recipient UPC | Fund Type | Amount of Transfer from Donor UPC | % of Change | Reason for Transfer
1 | Bristol | Miscellaneous | BRISTOL STP SAFETY/HES BALANCE ENTRY | -16921 | Bristol | Primary | Alt 58 Shoulder Imitative Wise County | 107120 | Highway Safety Improvements:Federal; Highway Safety Improvements:Soft Match | 791279 | 99.72% | Transfer of surplus funds recommended by District and Traffic Engineering Division from the District Safety Balance Entry line item to a scheduled project.
2 | Bristol | Primary | US 19 - Install Paved shoulders and rumble strips | 104671 | Bristol | Primary | Alt 58 Shoulder Imitative Wise County | 107120 | Highway Safety Improvements:Federal; Highway Safety Improvements:Soft Match | 817267 | 39.84% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to a scheduled project.
3 | Bristol | Primary | US 19 Paved Shoulders and Rumble Strips - Russell / Tazewell | 105470 | Bristol | Primary | US 460 / US 19 Overlap Shoulder Imitative - Tazewell County; Alt 58 Shoulder Imitative Wise County | 107119; 107120 | Highway Safety Improvements:Federal; Highway Safety Improvements:Soft Match; Open Container Funds:Statewide | 847702 | 17.29% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to a scheduled project.
4 | Bristol | Primary | US 23 Install Paved Shoulders and Rumble Strips | 106572 | Bristol | Primary | US 460 / US 19 Overlap Shoulder Imitative - Tazewell County | 107119 | Highway Safety Improvements:Federal; Highway Safety Improvements:Soft Match; Highway Safety Improvements:State Match; Open Container Funds:Statewide | 1056472 | 24.3% | Transfer of surplus funds recommended by District and Traffic Engineering Division from an underway project to a scheduled project.
5 | Bristol | Secondary | Rt.714 - Upgrade to Flashing Lights and Gates | 105551 | Statewide | Miscellaneous | STATEWIDE STP SAFETY/RAIL BALANCE ENTRY | 70704 | Rail Highway Crossings:State Match; Rail Highway Crossings:Statewide - Federal | 100848 | 34.54% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to the Statewide Rail Safety Balance Entry line item.
6 | Culpeper | Miscellaneous | CULPEPER STP SAFETY/HES BALANCE ENTRY | -16920 | Culpeper | Primary | RTE 29/718 - Intersection Improvements | 104805 | Highway Safety Improvements:Federal; Highway Safety Improvements:Soft Match | 259163 | 99.19% | Transfer of surplus funds recommended by District and Traffic Engineering Division from the Statewide Safety Balance Entry line item to a scheduled project.
7 | Culpeper | Primary | Route 211 Centerline Rumble Strip Project | 89667 | Statewide | Miscellaneous | STATEWIDE STP SAFETY/HES BALANCE ENTRY | 70700 | Safety Funds:Hazard Elimination | 26504 | 46.6% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to the Statewide Safety Balance Entry.
8 | Culpeper | Primary | Curve1-Shoulder Widening 0.06 Mi. E. of Monticello Loop | 96936 | Culpeper | Primary | Curve 2-Shoulder Widening 0.4 mi. E. of Monticello Loop; RTE 29/718 - Intersection Improvements | 96935; 104805 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 73920 | 22.54% | Transfer of surplus funds recommended by the District and Traffic Engineering Division from a completed project to fund a completed project and a scheduled project.
9 | Culpeper | Primary | WIDEN SHOULDER TO IMP. FREE FLOW RIGHTS, UPGRADE GR & SIGN. | 96937 | Culpeper | Primary | RTE 29/718 - Intersection Improvements | 104805 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 40501 | 14.77% | Transfer of funds recommended by the District and Traffic Engineering Division from a completed project to a scheduled project.
10 | Hampton Roads | Interstate | HAMPTON ROADS THIRD CROSSING - (PE ONLY) | 12834 | Hampton Roads | Interstate | Hampton Roads Crossing Study Supplemental EIS | 106724 | SAFETEA-LU Earmarks:Federal; SAFETEA-LU Earmarks:State Bond Match | 6352527 | 42.49% | Transfer of surplus funds recommended by District from a cancelled project to a scheduled project.
11 | Hampton Roads | Secondary | Stokes Rd over Magus Mill Pond Va struc 6054 | 85946 | Hampton Roads | Secondary | Rte 1304 (Wallace Rd) Bridge Replacement over West Ridge Ck | 98822 | STP:Bridge - Federal; STP:STP Bridge - Soft Match | 156250 | 26.02% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a scheduled project to fund a scheduled project.
12 | Hampton Roads | Secondary | Rte 1306 (School Ln) Bridge Replacement over West Ridge Ck | 98821 | Hampton Roads | Primary | RTE 58 BUSINESS BRIDGE (Carrsville) over Rte. 632 and CSX | 81435 | CTB Formula:Bridge - State | 117473 | 18.28% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a scheduled project to fund a scheduled project.
13 | Hampton Roads | Secondary | Rte 1304 (Wallace Rd) Bridge Replacement over West Ridge Ck | 98822 | Hampton Roads | Primary | RTE 58 BUSINESS BRIDGE (Carrsville) over Rte. 632 and CSX | 81435 | CTB Formula:Bridge - State | 170000 | 28.04% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a scheduled project to fund a scheduled project.
14 | Hampton Roads | Secondary | Bridge Replacement Rte 601 over Diascund Creek, Fed ID 10516 | 98823 | Hampton Roads | Primary | RTE 58 BUSINESS BRIDGE (Carrsville) over Rte. 632 and CSX | 81435 | CTB Formula:Bridge - State | 103345 | 15.32% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a scheduled project to fund an underway project.
15 | Hampton Roads | Secondary | Bridges ( FED ID 18304 18305, 18306) Over Blackwater River | 104009 | Hampton Roads | Secondary; Urban | Bridge street over Salters Creek VA Str. 8009; Rte 1306 (School Ln) Bridge Replacement over West Ridge Ck | 93081; 98821 | STP:Bridge - Federal; STP:BROS - Federal; STP:BROS - Soft Match; STP:STP Bridge - Soft Match | 706245 | 17.46% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from scheduled project to an underway and a scheduled project.
16 | Salem | Primary | RTE. 220 Bus. - Replace Signal at Int. Rtes. 667 and 1133 | 98384 | Salem | Miscellaneous | DISTRICTWIDE ROADWAY SAFETY ASSESSMENT - SALEM | 81419 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 74317 | 19.98% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to an underway project.
17 | Salem | Primary | RTE 220 Corridor - Safety Improvements to Box Culverts | 105360 | Salem | Miscellaneous | DISTRICTWIDE ROADWAY SAFETY ASSESSMENT - SALEM | 81419 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 97721 | 75.17% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to an underway project.
18 | Salem | Urban | RTE 460 - Install Flashing Beacons and Warning Signs | 100663 | Salem | Miscellaneous | DISTRICTWIDE ROADWAY SAFETY ASSESSMENT - SALEM | 81419 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 53978 | 25.11% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to an underway project.
19 | Staunton | Primary | Rte 39 Over Maury River, VA Str. 1046 | 90188 | Staunton | Secondary | RTE663– Replace Bridge 17172 & Appr over NF Shenandoah River | 82769 | Bridge Replacement:Federal; Soft Match:Federal | 400000 | 22.87% | Transfer of surplus funds recommended by District and Structure and Bridge Division from a scheduled project to fund an underway project.

## L10
Row | District Donor Project | System Donor Project | Description Donor Project | Donor UPC | District Recipient Project | System Recipient Project | Description Recipient Project | Recipient UPC | Fund Type | Amount of Transfer from Donor UPC | % of Change | Reason for Transfer
A | Bristol | Secondary | 0611-095-6011 Superstructure Replacement Fed Id 19000 | 86479 | Bristol | Secondary | Bridge Replacement | 87918 | Bridge Replacement:Federal; Soft Match:Federal | 2108 | 0.2012% | Transfer of surplus funds recommend by the District and Structure and Bridge Division from an underway project to a completed project.
B | Bristol | Secondary | Bridge Replacement | 87918 | Bristol | Secondary | Ruby's Rd over Little Walker Creek #6 (Fed. ID 3040) | 86596 | Federal STP:Federal; Soft Match:Federal | 54703 | 8.66% | Transfer of surplus funds recommended by the District from a completed project to an underway project.
C | Culpeper | Primary | Construct Right Turn Bay at Route 729 Milton Road | 96939 | Culpeper | Primary | RTE 29/718 - Intersection Improvements | 104805 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 33273 | 3.444% | Transfer of surplus funds recommended by District and Traffic Engineering Division from a completed project to a scheduled project.
D | Hampton Roads | Public Transportation | Amtrak Station Relocation - Amtrak Multimodal Station Reloc | 102734 | Hampton Roads | Urban | Continue to extend sidewalk along Rte 460 (N. Main St). | 99172 | CMAQ:MPO - Federal; CMAQ:MPO - State Match | 36621 | 0.0965% | Transfer of surplus funds recommended by District and MPO from a scheduled project to an underway project.
E | Hampton Roads | Secondary | Bridge (Fed ID 17757) Rte 308 Over Three Creek | 104965 | Hampton Roads | Primary | RTE 58 BUSINESS BRIDGE (Carrsville) over Rte. 632 and CSX | 81435 | CTB Formula:Bridge - State | 100000 | 2.59% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a scheduled project to fund a scheduled project.
F | Hampton Roads | Urban | Bridge street over Salters Creek VA Str. 8009 | 93081 | Hampton Roads | Primary | RTE 58 BUSINESS BRIDGE (Carrsville) over Rte. 632 and CSX | 81435 | CTB Formula:Bridge - State | 500384 | 9.764% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a scheduled project to fund a scheduled project.
G | Hampton Roads | Urban | Harbor View Area Traffic Signal Coordination | 100603 | Hampton Roads | Urban | Continue to extend sidewalk along Rte 460 (N. Main St). | 99172 | CMAQ:MPO - Federal; CMAQ:MPO - State Match | 56000 | 1.6% | Transfer of surplus funds recommended by District and MPO from a scheduled project to an underway project.
H | Hampton Roads | Urban | Primary Extension Paving - Clay Street | 107723 | Hampton Roads | Urban | Primary Extension Paving - South Street | 107722 | CTB Formula:Paving for Primary Extensions | 9930 | 4.413% | Transfer of surplus funds recommended by the District and Local Assistance Division from an underway project to fund an underway project.
I | Richmond | Primary | RTE 288- UPGRADE PAVEMENT MARKINGS TO B6 TAPE | 89449 | Richmond | Secondary | RTE 604 - REPLACE GUARDRAILS | 106238 | Safety Funds:Hazard Elimination | 22609 | 4.364% | Transfer of surplus funds recommended by the District and Traffic Engineering Division from a completed project to an underway project.
J | Richmond | Secondary | RTE 718 - BRIDGE REPLACEMENT | 97690 | Richmond | Secondary | RTE 633 - BRIDGE REPLACEMENT (FED ID 11978) | 93090 | Bond Match:State Bond Match; Bridge Replacement:Federal | 262 | 1.499% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a completed project to a scheduled project.
K | Salem | Primary | RTE. 221 OVER PINE CREEK (STR. 07492) - BRIDGE REPLACEMENT | 77298 | Salem | Primary | RTE. 116 OVER BACK CREEK (STR. 14928) - BRIDGE REPLACEMENT | 77305 | Bond Match:State Bond Match; Bridge Replacement:Federal | 79274 | 2.345% | Transfer of surplus funds recommended by the District and Structure & Bridge Division from a completed project to a scheduled project.
L | Staunton | Primary | Route 340 Bridge Replacement & Approaches over Gooney Creek | 76467 | Staunton | Secondary | RTE663– Replace Bridge 17172 & Appr over NF Shenandoah River | 82769 | STP:Bridge - Federal; STP:STP Bridge - Soft Match | 200000 | 1.07% | Transfer of surplus funds recommended by the District and Structure and Bridge Division from a completed project to an underway project.
M | Statewide | Miscellaneous | STATEWIDE STP SAFETY/RAIL BALANCE ENTRY | 70704 | Hampton Roads | Urban | E. Washington St.-Install Four Quad Flashing Lights & Gates | 100398 | Rail Highway Crossings:Federal; Rail Highway Crossings:State Match | 14 | 0.0006% | Transfer of surplus funds recommended by the District and Traffic Engineering Division from the Statewide Rail Safety Balance Entry line item to a completed project.
N | Statewide | Miscellaneous | STATEWIDE STP SAFETY/HES BALANCE ENTRY | 70700 | Culpeper; Hampton Roads; Northern Virginia | Interstate; Primary | SR20/SC611 signal installation; Install Curb & Gutter, Sidewalk and Upgrade Signal on US 50; RTE 29/718 - Intersection Improvements ; Route 58 Super Elevation Correction; I-64 WB Exit 296A Ramp Terminal Realignment | 95638; 96751; 104805; 107041; 107043 | Highway Safety Improvements:Federal; Highway Safety Improvements:Soft Match; Highway Safety Improvements:State Match; Safety Funds:Bike/Ped | 1068310 | 1.108% | Transfer of surplus funds recommended by the District and Traffic Engineering Division from the Statewide Safety Balance Entry line item to fund a completed project and scheduled projects.
O | Statewide | Primary | RTE. 220 Corridor Shoulder Widening & GR Install/Upgrades | 102738 | Salem | Miscellaneous; Primary | DISTRICTWIDE ROADWAY SAFETY ASSESSMENT - SALEM; Rt. 100 Giles County - Safety Improvements | 81419; 107051 | Highway Safety Improvements:Federal; Highway Safety Improvements:State Match | 273984 | 5.635% | Transfer of surplus funds recommended by the District and Traffic Engineering Division from a completed project to fund an underway and scheduled project.